ACTION PLAN

LONG-TERM GOALS (1 to 3 YEARS) FOR ESL/BASIC SKILLS:

DISTRICT:  Ventura County Community College District

Representative:  _______________________________________

COLLEGE:  Oxnard College

Representative:  _______________________________________

ESL/BASIC SKILLS (Due on or before October 15, 2009), District:  Ventura County Community College District

Action Plan for 2009 through 2012				College:  Oxnard College

| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| --- | --- | --- | --- | --- |
| A Organizational/ Administrative Practices | Continued Basic Skills Coordinator Position (reduced AY 2009-2010 from 60% to 40% release time) | A.3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). A.3.3 A designated budget allocation exists for developmental education. A.3.4 Formal mechanisms exist to facilitate communication/coordination between faculty and staff in different developmental disciplines as well as with student services. A.3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. | Aug. 17, 2009 | Dean of Liberal Studies; Basic Skills Coordinator; Transitional Studies Advisory Committee |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
|  | Continued Math Coordinator Position (reduced AY 2009-2010 from 60% to 20% release time for Fall and 40% release time for Spring) | A.3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). A.3.3 A designated budget allocation exists for developmental education. A.3.4 Formal mechanisms exist to facilitate communication/coordination between faculty and staff in different developmental disciplines as well as with student services. A.3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. | Aug. 17, 2009 | Dean of Liberal Studies; Dean of Math and Science; Math Coordinator; Transitional Studies Advisory Committee |
| A (continued) | Establish a Coordinator for the Success Academy (a basic skills math and English lab) (20% release time) | A.3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). A.3.3 A designated budget allocation exists for developmental education. A.3.4 Formal mechanisms exist to facilitate communication/coordination between faculty and staff in different developmental disciplines as well as with student services. A.3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. | Aug. 17, 2009 | Dean of Liberal Studies; Dean of Math and Science; Success Academy Coordinator; Transitional Studies Advisory Committee |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| A Organizational/ Administrative Practices (continued) | Publish description of Transitional Studies in Educational Master Plan including mis-sion and goals | A.2.1 A detailed statement of the mission for developmental education is clearly articulated. A.2.2 Diverse institutional stakeholders are involved in developing the developmental educa-tion mission, philosophy, goals, and objectives. A.2.4 Developmental education goals and objectives are clearly communicated across the institution. | October 2009 | Transitional Studies Advisory Committee; Basic Skills Coordinator; Dean of Liberal Studies; EVP |
| A (continued) | Establishment of program-level-type rubric for SLOs for Transitional Studies and agreement re assessment of same | A.2.2 Diverse institutional stakeholders are involved in developing the developmental education mission, philosophy, goals, and objectives. | August 2009 = establishment of program SLOs November 2009 = agreement re assessment of same | Transitional Studies Advisory Committee; Basic Skills Coordinator; Dean of Liberal Studies; SLO Coordinators; Instit. Researcher |
| A (continued) | Establishment of Transitional Studies Website | A.3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. | July 2009 and ongoing update | Basic Skills Coordinator; Dean of Liberal Studies; Transitional Studies Advisory Committee |
| A (continued) | Planning for Greater Centralization of Basic Skills Support | A.3.1 A clear institutional decision exists regarding the structure of developmental education (centralized or decentralized, but highly coordinated) | July 2009 and ongoing | Transitional Studies Advisory Committee; Dean of Liberal Studies; Success Academy |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
|  |  | A.4.3 Mechanisms/cultures exist to alleviate potential marginalization or stigma attached with isolation of basic skills students. A.5.3 A comprehensive learning assistance center provides support to developmental education students. A.5.4 Peers and/or faculty provide mentoring to developmental education students. |  | Coordinator |
| B Program Components | Regular Program Evaluations | B.2.2 Formative program evaluation activities occur on a regular basis. B.2.3 Summative program evaluation activities occur on a regular basis. | November 2009 | Dean of Liberal Studies; Dean of Math and Science; Program Effective-ness and Planning Committee (PEPC) |
| B (continued) | Ongoing analysis of data to evaluate success of Transitional Studies students as they progress through Transitional Studies curriculum to college level courses. | B.2.2 Formative program evaluation activities occur on a regular basis. B.2.3 Summative program evaluation activities occur on a regular basis. B.2.4 Multiple indices exist to evaluate the efficacy of developmental educational courses and programs. B.2.5 Data obtained from course/program evaluation are disseminated and used for future planning and continuous improvement. | Baseline data established and presented for interpretation on 3.26.09 Ongoing Transitional Studies Advisory Committee meetings | Executive Vice President; Dean of Liberal Studies; Dean of Math and Science; PEPC; Transitional Studies Advisory Committee; Dean of Educational Services and Research |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| B Program Components (continued) | Support and plan for creation of “The First Year Experience” and implementation of same | B.1.1 Mandatory orientation exists for all new students. B.1.4 Expanded pre-enrollment activities exist for students placed into developmental education courses. | AY 2009-2010 = creation/planning AY 2010-2011 = implementation | Dean of Student Services; Transitional Studies Advisory Committee; Counselors; Director of STEM Grant; Director of Title V; Executive Vice President |
| B (continued) | Secure Hiring of Matriculation Specialist (Bilingual) (abandoned due to budget cuts) | B.3.1 A proactive counseling/advising structure that includes intensive monitoring and advising serves students placed into developmental education courses. | Fall 2010 | Dean of Student Services; Transitional Studies Advisory Committee; Dean of Liberal Studies |
| C Faculty and Staff Development | Continue Faculty Summer Institute | C.1.2 Professional development activities for developmental education faculty and staff are actively supported by senior administration. C.2.1 Developmental education faculty are involved in the design, planning, and implementation of staff development activities related to developmental education. C.2.2 Developmental education staff development activities address both educational theory and practice. C.2.6 Staff development activities promote interactions among instructors. | First Faculty Summer Institute, May 26-27, 2009 Second Faculty Summer Institute planned for end of May, 2010 | Dean of Liberal Studies; Basic Skills Coordinator; Transitional Studies Advisory Committee; Professional Development Committee; Executive Vice President |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| C Faculty and Staff Development (continued) | Continue Faculty Summer Institute (continued) | C.5.2 Opportunities exist for colleagues across disciplines to engage in interchanges that foster a “culture of teaching,” which in turn develops a “community of scholars.” C.5.3 The institution expresses value for staff development activities through provision of extrinsic rewards where appropriate (e.g., funding, time, salary advancement, or formal recognition of achievement). |  |  |
| C (continued) | Meetings/ Workshops re entry and exit skill alignment for ESL, English and Math course sequences | C.2.2 Developmental education staff development activities address both educational theory and practice. C.2.3 Staff development activities are widely attended and viewed as valuable by developmental education faculty and staff. C.2.4 The staff development program for develop-mental educators is regularly evaluated by partici-pants, and data collected are sued for continuous improvement. C.2.6 Staff development activities promote interactions among instructors. | Monthly, Letters and Math Department meetings; August 14, 2009 Flex Activity; Nov. 2009 Flex Activity; Fall 2009 Meetings of ESL Faculty | Basic Skills Coordinator; Dean of Liberal Studies; Transitional Studies Advisory Committee; Letters Dept.; Math Dept.; Math Coordinator |
| C (continued) | Continue to hire and train paraprofessionals and tutors for work in the Success Academy/ Referral Program (albeit with a reduced number for AY 2009-2010) | C.4.1 Peer Mentoring C.4.2 Instructional Consultation | July 2009 Fall 2010 | Dean of Liberal Studies; Members of Transitional Studies Advisory Committee; Director of Tutoring; Success Academy Coord. |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| C Faculty and Staff Development | Attendance at various conferences pertinent to transitional studies and reporting back best practices | C.4.4 Scholarship of Teaching and Learning | 2/20/09: CTE BSI Workshop 3/11-12/09: BSI CTE Workshop 2/26/09: WASC Assessment Workshop 4/16-18/09: CATESOL 4/24/09: SBCC BS Workshop 5/29-31/09: Chaffey College BS Boot Camp 9/17-18/09: BS Coordinators Workshop Fall 2009 BSI-sponsored Workshops 3/10-13/09: NADE | Transitional Studies Advisory Committee; Basic Skills Coordinator; Dean of Liberal Studies; Dean of Math and Science; Math Coordinator |

| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| --- | --- | --- | --- | --- |
| D Instructional Practices | Faculty Summer Institutes | D.1.2 Problem-solving and critical-thinking skills are integrated into developmental education curriculum D.1.3 Developmental education curriculum recognizes and emphasizes the cognitive development of students (e.g., contextualized learning, metacognitive skill development and constructivism). D.3.1 In classroom teaching/learning, attention is paid to students’ attitudes and emotions (e.g., self-concept and self-efficacy development) as well as to teaching basic subject skills. D.4.1 Instructional content and pedagogy capitalize on perspectives and life experiences of students from diverse backgrounds. D.4.2 Developmental instruction communicates high expectations, engages students in critical dialogue regarding cultural conflicts, and establishes compatible sociocultural contexts for group learning. D.6.1 Instructors in developmental education courses assess, employ, and incorporate a variety of active learning strategies (e.g., student engagement, collaborative learning, learning communities, supplemental instruction, and service learning). D.8.2 Formal processes exist that facilitate and promote the exchange of effective instructional strategies among faculty across disciplines. | First Faculty Summer Institute: May 26-27, 2009 Second Faculty Summer Institute planned for end of May, 2010 | Basic Skills Coordinator; Dean of Liberal Studies; Transitional Studies Advisory Committee; Professional Development Committee; Professional Development Committee; Executive Vice President |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| D Instructional Practices (continued) | Regular Reporting Out of Best Practices Gained from Conference Attendance and Reading Latest Published Research | D.8.1 Formal processes exist that facilitate and promote the exchange of effective instructional strategies among faculty within disciplines. | Monthly at Transitional Studies Advisory Committee Meetings | Transitional Studies Advisory Committee |
| D (continued) | Integration of Learning Center Resources Across the Curriculum (emphasizing materials that have proven most successful) with T.S. students. | D.1.1 Developmental education focuses on self-directed learning, with students engaged in actively assessing and monitoring their own motivation and learning. D.2.2 Developmental courses/programs implement effective curricula and practices for mathematics (e.g., addressing environmental factors, problem-based learning, small group instruction, contextual learning, appropriate use of technology, and learning labs). | April 2009 Plato Training Sessions Continuous Learning Center Training Sessions Fall 2009 | Transitional Studies Advisory Committee; Dean of Liberal Studies; Learning Center Personnel; Basic Skills Coordinator |
| D (continued) | Piloting of Referral Program for all students needing writing assistance | D.2.3 Developmental courses/programs implement effective curricula and practices for ESL D.3.4 Formal mechanisms in developmental courses and programs enhance student motivation and engagement to promote learning. | Spring 2009 Fall 2009 | Success Academy Paraprofessional; Basic Skills Coordinator; Transitional Studies Advisory Committee |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| D Instructional Practices (continued) | Entry/Exit Skill Alignment Workshops | D.5.1 A well-planned, step-by-step sequence of developmental education course offerings exists. D.7.1 Developmental education course entry/exit standards are regularly reviewed and revised as needed. D.7.2 The entire trajectory of developmental course sequences (including entry by placement instruments) is periodically reviewed and aligned to ensure appropriate student progression through sequential levels. D.7.3 A systematic approach exists within disciplines to align developmental education course content and pedagogy to degree-applicable and transfer-level course content. | Monthly at Letters and Math Department Meetings August 14, 2009 Flex Activity November 2009 Flex Activity ESL Faculty Meetings, Fall 2009 | Transitional Studies Advisory Committee; Dean of Liberal Studies; Dean of Math and Science; Basic Skills Coordinator; Math Coordinator |
| D (continued) | Utilizing Supplemental Instruction in targeted Transitional Studies high-risk classes | D.6.1 Instructors in developmental education courses assess, employ, and incorporate a variety of active learning strategies (e.g., student engagement, collaborative learning, learning communities, supplemental instruction, and service learning). D.10.3 Various learning support services provide active learning experiences (e.g., supplemental instruction, workshops, and study groups). | Spring 2010 | Transitional Studies Advisory Committee; Dean of Liberal Studies; Dean of Student Services |

| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| --- | --- | --- | --- | --- |
| D Instructional Practices (continued) | Creation of Modularized Versions (ala Success Academy) of ENGL R096 | D.1.1 Developmental education focuses on self-directed learning, with students engaged in actively assessing and monitoring their own motivation and learning. D.1.2 Problem-solving and critical-thinking skills are integrated into developmental education curriculum. D.1.3 Developmental education curriculum recognizes and emphasizes the cognitive development of students (e.g., contextual learning, metacognitive skill development, and constructivism). D.2.1 Developmental courses/programs implement effective curricula and practices for English (e.g., reading/writing integration, writing across the curriculum, and use of writing labs). D.5.1 A well-planned, step-by-step sequence of developmental education course offerings exists. D.5.3 Individual courses (particularly those taken earliest in the developmental sequence) engage students in highly structured learning experiences designed to progressively build their skills and knowledge. | Spring 2010 | Teresa Bonham; Curriculum Committee; Letters Department; Transitional Studies Advisory Committee; Dean of Liberal Studies |
| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| D Instructional Practices (continued) | Collection of biographical essays from ESL students to be initially published online, then made available as a printed publication, and finally presented live in a readers’ theater format | D.3.1 In classroom teaching/learning, attention is paid to students’ attitudes and emotions (e.g., self-concept and self-efficacy development) as well as to teaching basic subject skills. D.3.5 College programs promote basic skills students’ social integration into and identification with the college environment. D.4.1 Instructional content and pedagogy capitalize on perspectives and life experiences of students from diverse backgrounds. D.6.2 Developmental education promotes individualized student learning, focusing on learner-centeredness rather than teacher-centeredness. D.6.3 The academic and campus climate supports active learning strategies and connects developmental education students to the institution, faculty, staff, and other students. | Online publication: Spring 2010 Printed publication: Fall 2010 Readers’ Theater presentation: Fall 2011 | Transitional Studies Advisory Committee; Dean of Liberal Studies; ESL Instructors; Chair of Performing Arts |

| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/ Department(s) |
| --- | --- | --- | --- | --- |
| D Instructional Practices (continued) | Publication Online of an Oxnard College Literary Magazine for Developmental Educational Students | D.3.1 In classroom teaching/learning, attention is paid to students’ attitudes and emotions (e.g., self-concept and self-efficacy development) as well as to teaching basic subject skills. D.3.5 College programs promote basic skills students’ social integration into and identification with the college environment. D.4.1 Instructional content and pedagogy capitalize on perspectives and life experiences of students from diverse backgrounds. D.4.2 Developmental instruction communicates high expectations, engages students in critical dialogue regarding cultural conflicts, and establishes compatible sociocultural contexts for group learning. D.4.3 Developmental instruction reflects cultural sensitivity and culturally mediated instruction (e.g., the way communication and learning takes place in students’ cultures). | Fall 2010 | Transitional Studies Advisory Committee; Dean of Liberal Studies; Letters Department; Eric Boyz; Oxnard College Foundation |