- ACTION PLAN

LONG TERM GOALS (1 to 3 YEARS) FOR ESL/BASIC SKILLS:

District:  VCCCD Representive:_______________________________________________

College:  Oxnard College Representative:______________________________________

ESL/Basic Skills (Due on or before May 1, 2008) District: Ventura Community College District

Action Plan for 2008 through 2010			College: Oxnard College

| Section | Planned Action | Effective Practice and Strategy | Target Date for Completion | Responsible Person(s)/Department(s) |
| --- | --- | --- | --- | --- |
| A Organizational/Administrative Practices | Establish a “Developmental Mathematics Facilitator/ Coordinator Establish a “Network for English Transition /NET” facilitator position. Evaluate centralization, linkage and delivery of Basic Skills centers. Hire a ESL/ Basic Skills Initiative Project Dean of Liberal Studies and Dean of Math & Science and Clerical Support person. Establish permanent Advisory Committee | A3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). A3.3 A designated budget allocation exists for developmental education. A3.4 Formal mechanisms exist to facilitate communication/coordination between faculty and staff in different developmental disciplines as well as with student services. A3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. A3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). A3.3 A designated budget allocation exists for developmental education. A3.4 Formal mechanisms exist to facilitate communication/coordination between faculty and staff in different developmental disciplines as well as with student services. A3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. A.1 Developmental education is a clearly stated institutional priority A3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). A3.3 A designated budget allocation exists for developmental education. A3.4 Formal mechanisms exist to facilitate communication/coordination between faculty and staff in different developmental disciplines as well as with student services A3.5 Formal mechanisms exist to facilitate communication/coordination between pre-collegiate and college-level faculty within disciplines. A3.2 Based upon the institutional structure, a dedicated administrator or lead faculty is/are clearly identified and accorded responsibility for college-wide coordination of basic skills program(s). | July 1, 2008 July 1, 2008 Dec. 2008 July 1, 2008 May 1, 2008 | Dean of Math and Sciences, & VP of Instruction Dean of Liberal Studies & VP of Instruction Dean of Liberal Studies, Dean of Math and Sciences and VP of Instruction Dean of Liberal Studies & VP of Instruction VP of Instruction with assistance of BSI task force |
| B Program Components | Regular Program Evaluations. Ongoing analysis of data to evaluate success of Basic Skills Students as they progress through Basic Skills curriculum to college level courses. Improve assessment tools to measure student success goals Development of Success Academy for Math and English Basic Skills. | B2.2Formative program evaluation activities occur on a regular basis. B2.3 Summative program evaluation activities occur on a regular basis. B2.2 Formative program evaluation activities occur on a regular basis. B2.3 Summative program evaluation activities occur on a regular basis. B2.4 Multiple indices exist to evaluate the efficacy of developmental education courses and programs. B2.5 Data obtained from course/program evaluation are disseminated and used for future planning and continuous improvement. B2.1 Developmental education course content and entry/exit skills are regularly reviewed and revised as needed. B2.5 Data obtained from course/program evaluation are disseminated and used for future planning and continuous improvement. | April 1, 2008 and yearly May 2007 August 2007 | Dean of Liberal Studies and Dean of Math and Sciences with PEPC Committee assistance; Advisory Committee; Basic Skills Initiative Project Dean of Liberal Studies and Dean of Math & Science; Dean of Institutional Research. Basic Skills Initiative Dean of Liberal Studies and Dean of Math & Science and BSI Advisory Committee Activity Coordinator from Title V, Dean of Liberal Studies and Dean of Math & Science, Director of Title V, V.P. of Instruction, |
| C Faculty and Staff Development | Regional/District Basic Skills 1 Training Retreat Workshop: Internal education integrating success academy instructional activities with Basic Skills. Establish regular meetings with ESL/basic skills faculty to discuss issues and current curriculum. Hire and train Para Professionals and tutors in ESL/Basic Skills teaching service Examination of best practices in basic skills which facilitated the design and creation of the Success Academy Look at model programs of ESL/Basic Skill delivery systems at model campuses for possible incorporation at this campus. Seminars & Conferences Develop certified faculty in certified education such as National Developmental Education University of South Carolina; Summer Certificate Program; get Project Director Dean of Liberal Studies and Dean of Math & Science and other people certified. Link with High School Basic Skills delivery via a Saturday Bridge Program Identify links to 4 year Institutions in offering Basic Skills and remediation education on their sites | C2.1 Developmental education faculty are involved in the design, planning, and implementation of staff development activities related to developmental education. C2.2 Developmental education staff development activities address both educational theory and practice. C2.5 New faculty are provided staff development activities that assist them in transitioning into the community college academic environment. C2.6 Staff development activities promote interactions among instructors. C2.2 Developmental education staff development activities address both educational theory and practice. C2.3 Staff development activities are widely attended and viewed as valuable by developmental education faculty and staff. C4.1 Peer Mentoring C4.2 Instructional Consultation C4.4 Scholarship of Teaching & Learning. C4.4 Scholarship of Teaching & Learning C4.6 Great Teacher Seminars C4.4 Scholarship of Teaching & Learning C4.6 Great Teacher Seminars C4.7 Academic Alliances (e.g., K-16 Inter-Segmental Partnerships) C4.7 Academic Alliances (e.g., K-16 Inter-Segmental Partnerships) | Aug. 8, 2007 March 14, 2008 Fall 2008 Flex Week, August 2008 March 14, 2008 Flex Week August 2008 October & December 2008 February 2009 May 2009 June 1, 2008 February 2007 March 17, 2007 November 7-9, 2007, ongoing. April 2008 Met with Marsha Elliott and in Feb. 2007, visited 5 of the best basic skills centers in CA. Attended the Assn. of Community and Continuing Education Conference, Feb. 2007. In Mar. 2007, visited Community College of Denver. Facilitated training from Jun. – Oct. 2007 April 2008 June 22-27, 2008 – Ongoing October 2008 April 2008 June 22-27, 2008 – Ongoing October 2008 Fall 2008 Dec. 2008 | Activity Coordinator from Title V; Dean of Liberal Studies and Dean of Math & Science of Title V; BSI Advisory Committee Dean of Liberal Studies, Dean of Math and Sciences, Title V Activity Coordinator Basic Skills Initiative Project Dean of Liberal Studies and Dean of Math & Science; Mathematics Facilitator; English Facilitator. Dean of Liberal Studies and Dean of Math & Science of Title V; Activity Coordinator. Title V Project Director Title V Project Dean of Liberal Studies and Dean of Math & Science, Dean of Liberal Studies, Dean of Math and Sciences Basic Skills Initiative Project Director Dean of Liberal Studies and Dean of Math & Science Basic Skills Initiative Project Director Dean of Liberal Studies and Dean of Math & Science Basic Skills Initiative Project Director Dean of Liberal Studies and Dean of Math & Science Dean Student Services – High School Partnership Coordinator Basic Skills Initiative Project Dean of Liberal Studies and Dean of Math & Science; Title V Director, and Area Deans. Dean of Liberal Studies and Dean of Math and Sciences |
| D Instructional Practices | Purchase and incorporate resources such as software, equipment , and other instructional aides, that is basic skills focused, ESL focused, and enhances the Learning Center and Success area. Use this software and equipment to further enhance basic skills training access for students. This is designed to further develop and enhance modular, drop in, and open enrollment practices for basic skills/ESL needs. Incorporate instructional practices that will assist in the transition of basic skills and study skills of students into college level classes. Hire Para-Professionals to support Success Academy and Learning Center. Development of Success Academy and enhancement of Learning Center for ESL skills. Coordinate integration of Success Academy and Learning Center as the alternative basic skills training options. | D6.1 Instructors in developmental education courses assess, employ, and incorporate a variety of active learning strategies (e.g., student engagement, collaborative learning, learning communities, supplemental instruction, and service learning). D6.2 Developmental education promotes individualized student learning, focusing on learner-centeredness rather than teacher-centeredness. D9.1 Mechanisms exist to frequently and consistently provide course performance feedback to students. D10.7 An academic support center provides diverse and active learning experiences such as workshops, study groups, self-paced instruction via video or software, and experiential learning. D1.3 Developmental education curriculum recognizes and emphasizes the cognitive development of students (e.g., contextual learning, metacognitive skill development, and constructivism). D2.2 Developmental courses/programs implement effective curricula and practices for mathematics (e.g., addressing environmental factors, problem-based learning, small group instruction, contextual learning, appropriate use of technology, and learning labs). D2.3 Developmental courses/programs implement effective curricula and practices for ESL D2.4 Developmental courses/programs implement effective curricula and practices for development of study skills. D10.5 Tutoring is available and accessible in response to student needs/desires. D1.1 Developmental education focuses on self-directed learning, with students engaged in actively assessing and monitoring their own motivation and learning. D2.1 Developmental courses/programs implement effective curricula and practices for English (e.g., reading/writing integration, writing across the curriculum, and use of writing labs). D2.4 Developmental courses/programs implement effective curricula and practices for development of study skills. D3.4 Formal mechanisms in developmental courses and programs enhance student motivation and engagement to promote learning. D5.1 A well-planned, step-by-step sequence of developmental education course offerings exists. D5.3 Individual courses (particularly those taken earliest in the developmental sequence) engage students in highly structured learning experiences designed to progressively build their skills and knowledge. D6.1 Instructors in developmental education courses assess, employ, and incorporate a variety of active learning strategies (e.g., student engagement, collaborative learning, learning communities, supplemental instruction, and learner-centeredness rather than teacher-centeredness. D6.2 Developmental education promotes individualized student learning, focusing on learner-centeredness rather than teacher-centeredness. D9.1 Mechanisms exist to frequently and consistently provide course performance feedback to students. D9.2 Faculty and advising staff provide early intervention and support to students experiencing academic and/or personal difficulties. D10.5 Tutoring is available and accessible in response to student needs/desires. D10.6 All tutors receive formal training in both subject matter and effective pedagogy for the discipline. D10.7 An academic support center provides diverse and active learning experiences such as workshops, study groups, self-paced instruction via video or software, and experiential learning. | March 30, 2008 and ongoing April 8, 2007 (Division Meeting), ongoing July 1, 2008 August 2007 Success Academy launch March 13, 2008 Learning Center software and materials enhancement. | Project Dean of Liberal Studies and Dean of Math & Science Basic Skills Initiative Basic Skills Project Director, Dean of Liberal Studies, Dean of Math & Science, Dean of Student Services Dean of Liberal Studies Title V Coordinator Title V Dean of Liberal Studies and Dean of Math & Science Title V Coordinator Title V Director, Dean of Liberal Studies and Dean of Math & Science |